## old
Phase | Start date | End date | Days | Name | Task | Note
I (Validation Programs & Manual) | 2016-05-18 | 2016-05-27 | 8 | Allen | (1) Update checking programs (2) Refresh ‘Janssen SDTM Validation Process Manual’ per review comment | Elodie/jingjing: could get familar with these macros
| 2016-05-30 | 2016-06-03 | 5 | Elodie/Jingjing | (1) Validate check programs using dataset (2) Review ‘Janssen SDTM Validation Process Manual’ Prepare the training slide for check macros (including but not limited: how to use and how to review the report), send it to Allen and Jingjing for review | Validation & update could proceed paralleled.
| 2016-06-06 | 2016-06-08 | 3 | Allen | (1) Update checking programs if any comment (2) Refresh ‘Janssen SDTM Validation Process Manual’ if any comment
| 2016-06-12 | 2016-06-14 | 3 | Shenglin/Brian/Annie | Please provide comment on ‘Janssen SDTM Validation Process Manual’
| 2016-06-15 | 2016-06-17 | 3 | Allen | (1) Update ‘Janssen SDTM Validation Process Manual’ if any comment (2) Re-submit updated version to review until no any comments
2 (Training Slide) | 2016-06-20 | 2016-06-24 | 5 | Elodie | Draft ‘Janssen SDTM Validation Training’ based on Manual
| 2016-06-27 | 2016-06-28 | 2 | Allen/Jingjing | Review training slide and give comment to Elodie
| 2016-06-29 | 2016-06-30 | 2 | Elodie | Incorporate review comment
| 2016-07-01 | 2016-07-04 | 2 | Shenglin/Brian/Annie | Review Training slide and provide comment
| 2016-07-05 | 2016-07-07 | 3 | Elodie | Incorporate review comment and until no more comment
3( Release Validation codes/Manual, Deliver Training) | After 2016-07-07 |  |  | Elodie/Allen/jingjing | Allen: (1) Relese Janssen SDTM validation programs (2) Release Janssen SDTM validation Manual
Elodie: Deliver the training
4 (Maintenance) |  |  |  | Allen/Elodie/jingjing | Regular maintain check programs/Manual, and keep users updated

## new
Phase | Start date | End date | Days | Name | Task | Note
I (Validation Programs & Manual) |  | 2016-07-27 |  | Allen | (1) Update checking programs (2) Refresh ‘Janssen SDTM Validation Process Manual’ per review comment
| 2016-08-13 |  |  | Pengfei/Jingjing | (1) Validate check programs using dataset (2) Review ‘Janssen SDTM Validation Process Manual’ Prepare the training slide for check macros (including but not limited: how to use and how to review the report), send it to Allen and Jingjing for review | Validation & update could proceed paralleled.
| 2016-06-06 | 2016-06-08 | 3 | Allen | (1) Update checking programs if any comment (2) Refresh ‘Janssen SDTM Validation Process Manual’ if any comment
| 2016-06-12 | 2016-06-14 | 3 | Shenglin/Brian/Annie | Please provide comment on ‘Janssen SDTM Validation Process Manual’
| 2016-06-15 | 2016-06-17 | 3 | Allen | (1) Update ‘Janssen SDTM Validation Process Manual’ if any comment (2) Re-submit updated version to review until no any comments
2 (Training Slide) | 2016-06-20 | 2016-06-24 | 5 | Elodie | Draft ‘Janssen SDTM Validation Training’ based on Manual
| 2016-06-27 | 2016-06-28 | 2 | Allen/Jingjing | Review training slide and give comment to Elodie
| 2016-06-29 | 2016-06-30 | 2 | Elodie | Incorporate review comment
| 2016-07-01 | 2016-07-04 | 2 | Shenglin/Brian/Annie | Review Training slide and provide comment
| 2016-07-05 | 2016-07-07 | 3 | Elodie | Incorporate review comment and until no more comment
3( Release Validation codes/Manual, Deliver Training) | After 2016-07-07 |  |  | Elodie/Allen/jingjing | Allen: (1) Relese Janssen SDTM validation programs (2) Release Janssen SDTM validation Manual
Elodie: Deliver the training
4 (Maintenance) |  |  |  | Allen/Elodie/jingjing | Regular maintain check programs/Manual, and keep users updated